## Goals
R E S E A R C H 2 0 0 5 - 2 0 1 0 S T R A T E G I C T H E M E S & G O A L S | R E S E A R C H 2 0 1 0 - 2 0 1 5 S T R A T E G I C T H E M E S & G O A L S
A. ENERGY & RESOURCES THEME | GOAL #
STRATEGIC GOALS: | 1 | Maximize the actual operational energy performance of buildings and facilities
A1. Provide guidance on techniques and move 30% towards net zero-energy use bldgs by 2008, 50% by 2012, and 70% by 2015
A2. Produce by 2015 new residential and light commercial bldgs that use 70% less energy based on ASHRAE 90.2-2001 | 2 | Progress toward Advanced Energy Design Guide (AEDG) and cost-effective net-zero-energy (NZE) buildings
A3. Develop by 2015 economically viable applications of renewable energy that reduce conventional energy usage by 25%
A4. Develop systems and components that reduce energy use in supermarkets by 30% by 2015 | 3 | To reduce significantly the energy consumption for HVAC&R, water heating and lighting in existing homes.
A5. Optimize & make consistent ASHRAE standards 90, 62, AND 55 for energy efficiency & IEQ for indoor built environments
A6. Develop integrated best practices design methods that optimize energy eff., life cycle cost, IEQ, and environmental impact | 4 | Significantly advance our understanding of the impact of indoor environmental quality (IEQ) on work performance, health symptoms and perceived
A7. Develop methods for measured bldg.(energy, cost, emissions) & occupant (comfort, health, productivity) performance. |  | environmental quality in offices, providing a basis for improvements in ASHRAE standards, guidelines, HVAC&R designs and operation practices.
A8. Establish benchmark data on energy use in industrial refrigeration
| 5 | Support the development of ASHRAE energy standards and reduce effort required to demonstrate compliance
B. INDOOR ENVIRONMENTAL QUALITY THEME
STRATEGIC GOALS: | 6 | Building Information Modeling (BIM) of energy efficient, high-performing buildings
B1. Make improvements in occupant health and comfort that yield 20% increase in productivity by 2015
B2. Provide optimal indoor environment for bldgs, vehicles, & facilities with respect to comfort, productivity, health, & safety | 7 | Support development of tools, procedures and methods suitable for designing low energy buildings
B3. Understand better how contagious viruses are transmitted in indoor environments and develop countermeasures
B4. Develop self-diagnostic inspection methods for HVAC systems that minimize impacts on comfort, health, & productivity | 8 | Facilitate use of natural and low global warming potential (GWP) synthetic refrigerants and seek methods to reduce refrigerant charge
C. TOOLS AND APPLICATIONS THEME | 9 | Support the development of improved HVAC&R components ranging from residential through commercial to provide improved system efficiency ,
STRATEGIC GOALS: |  | affordability, reliability and safety
C1. Develop more effective tools that will improve the productivity of the design process by 25% by 2015
C2. Develop dual path standards where paths are a) Prescriptive based, and b) Performance based | 10 | Significantly increase the understanding of energy efficiency , environmental quality and the design of buildings in engineering and architectural education
C3. Develop methods to allow a designer to accurately model a bldg in virtual reality in no more than 1 week by 2010
C4. Develop a measurement-based rating system to establish the environmental performance of a bldg & its systems | 11 | Understand influences of HVAC&R on airborne pathogen transmission in public spaces and develop effective control strategies
C5. Develop self-calibrating & low-cost sensor systems that measure control variables (comfort, health, productivity)
C6. Establish design tools to improve the installed energy eff. of HVAC&R systems and components
C7. Provide design guidance for bldgs. and systems to address the past and expected change in climatic conditions
D. EQUIPMENT, COMPONENTS & MATERIALS THEME
STRATEGIC GOALS:
D1. Establish techniques to improve energy eff. & reliability of HVAC&R components
D2. Continue research into new alternative and natural refrigerants
D3. Improve performance and reliability and minimize the environmental impacts of working fluids and materials
D4. Advance ASHRAE's role in the safety and security of food distribution
D5. Develop reliable, durable, and self-correcting sensor technology for monitoring IEQ, pollutants, energy conservation, & FDD
D6. Move one or more non-traditional technologies to market readiness by 2010
D7. Develop techniques that reduce the installed energy use of HVAC&R system auxiliary equipment 50% by 2015
E. EDUCATION & OUTREACH THEME
STRATEGIC GOALS:
E1. Make the results of ASHRAE research available to the technical committee
E2. Ensure that ASHRAE research has an international impact

## Current Plan
| A S H R A E R E S E A R C H I M P L E M E N T A T I O N P L A N |  |  |  |  | Annual 2018
# | TOPIC # | STATUS | RESPONSIBLE TC/TG | TITLE | EST. COST | EST. DURATION (Months) | RESEARCH STRATEGIC PLAN GOALS SUPPORTED | CO-SPONSOR TCs | 1st DRAFT OF WORK STATEMENT DUE TO RAC BY THIS DATE | RAC APPROVAL FOR BID REQUIRED BY THIS DATE OR DROPPED | DATE OF LAST SUBMISSION (YR.MO) | OBJECTIVE | Proposed Rating: None Low Medium Med.-High High | 0 pts 45 pts 135 pts 270 pts 405 pts | Rating: None: Low: Medium: High: | 0 pts 10 pts 30 pts 90 pts | Rating: None: e.g. missing info. Low: e.g. limited use & small improvement Medium: e.g. large use or large improvement High: e.g. large use and large improvement | 0 pts 15 pts 45 pts 135 pts | Rating: None: Low: Medium: High: | 0 pts 10 pts 30 pts 90 pts | Rating: None: Low: Medium: High: | 0 pts 15 pts 45 pts 135 pts | Rating: None or no support Low: Medium: Support High: Great Project! | 0 pts 5 pts 15 pts 45 pts | Total Score | FY 09-10 Draft Budget $2,913,200 | FY 10-11 Draft Budget TBD | FY 11-12 Draft Budget TBD | FY 12-13 Draft Budget TBD | FY 08-09 Budget $2,668,000
= | = | = | = | = | = | = | = | = | = | = | = |  | = | = | = | = | = | = | = | = | = | = | = | = | = | = |  | = |  | =
Research Project Funds Already Committed as of 1/1/10 | [25 empty] | 1689117 | 916712 | 216250 | 0 | 2504352
Additional Project Funds that could be Potentially Committed by April 2010 | [25 empty] | #REF! | #REF! | #REF! | #REF!
Solicited Research Projects That Could Potentially be Funded by annual 2018 Based upon Bids Received in winter 2018 or earlier:
1 | 1579 | TRP | 2.3 | TESTING AND EVALUATION OF OZONE FILTERS FOR IMPROVING IAQ | 191000 | 18 | #9 | EHC, SSPC 62.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
2 | 1707 | TRP | 2.6 | ANNOYANCE THRESHOLD OF TONES IN NOISE AS RELATED TO BUILDING SERVICES EQUIPMENT | 150000 | 18 | #4 | 2.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
3 | 1720 | TRP-R | 2.3 | VALIDATION OF GAS PHASE AIR-CLEANER PERFORMANCE TEST METHOD (STANDARD 145.2) BY LABORATORY TESTING OFCOMMERCIALLY AVIALABLE FILTRATION DEVICES | 150000 | 24 | #4 | SSPC 45, SSPC 62.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
4 | 1740 | TRP-R | 3.3 | HYDROGEN FLUORIDE CAPACITY OF DESICCANTS | 120000 | 9 | D1 | 3.2 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
5 | 1769 | TRP | 5.1 | EXPERIMENTAL EVALUATION OF THE EFFICIENCY OF BELT DRIVES FOR FANS | 120000 | 18 | #1 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
6 | 1778 | TRP | 5.1 | DEVLOPING DESING GUIDELINES FOR DISH ROOM VENTILATION | 135000 | 12 | #2, #7 | 4.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
7 | 1790 | TRP | 3.3 | DISTRIBUTION OF WATER BETWEEN VAPOR AND LIQUID PHASES OF LOW GWP REFRIGERANTS | 150000 | 12 | #8? | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
8 | 1794 | TRP | 3.1 | WHITE PAPER INVESTIGATION RELATING TO THE USE OF ODORANTS IN FLAMMABLE REFRIGERANTS. | 40000 | 4 | #8, #5, #9 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
9 | 1800 | TRP | 1.3 | SPRAY EVAPORATION ON ENHANCED TUBE BUNDLES WITH LOW GWP PURE REFRIGERANTS AND REFRIGERANT/MOSCIBLE OIL MIXTURES | 180000 | 30 | #8 | MTG.Low. GWP 8.5 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
10 | 1801 | TRP | 1.5 | STANDARDIZING AND UTILIZING ASHRAE ONLINE BIM DATA EXCHANGE PROTOCOLS | 125000 | 18 | #6, #1, #5, #7 | 7.1, MTG.BIM | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
11 | 1814 | TRP | 2.8 | ACTUAL ENERGY PERFORMANCE OF BUILDING DESIGNED TO COMPLY WITH ASHRAE STANDARD 90.1-2010 | 200000 | 18 | #1, #5, #7 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
12 | 1819 | TRP | 4.3 | CO2 DEMAND CONTROLLED VENTILATION IN MULTIPLE ZONE VAV SYSTEMS WITH MULTIPLE RECIRCULATION PATHS | 140000 | 18 | #1, #2, #5 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
13 | 1823 | TRP | 4.3 | IMPROVED EXHAUST-TO-INTAKE DILUTION (CONCENTRATION) CALCULATIONS | 75000 | 12 | #1, #2, #5, #7, #10, #11 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
Research Projects That Could Potentially Bid in the Fall 2018 or Spring 2019 - Rebids, Approved, and Conditionally Approved TRPs:
14 | 1683 | TRP-R | 1.3 | EXPERIMENTAL EVALUATION OF TWO-PHASE PRESSURE DROP AND FLOW IN U-BENDS WITH AMMONIA | 150000 | 30 | #8 | 8.4 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
15 | 1780 | TRP | 2.3 | TEST METHOD TO EVALUATE CROSS-CONTAMINATION OF GASEOUS CONTAMINANT WITHIN TOTAL ENERGY RECOVERY DEVICES | 125000 | 15 | #9 | 9.6, 2.3, SSPC 62.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
16 | 1784 | TRP-C | 2.4 | REPEATABILITY AND REPRODUCIBILITY ASSESSMENT OF ASHRAE STANDARD 52.2 AS CURRENTLY AMENDED | 195000 | 18 | #4 | SSPC52.2 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
17 | 1789 | TRP-C | 4.5 | OPTICAL AND THERMAL PERFORMANCE OF HOLLOW GLASS BLOCKS | 130000 | 18 | #1, #7 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
18 | 1810 | TRP-C | 7.5 | DETECTION AND DIAGNOSIS OF LEAKAGE FOR GROUND SOURCE HEAT PUMP SYSTEMS (GSHP) | 125000 | 24 | #6 | BIM.MTG | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
19 | 1830 | TRP-C | 9.3 | EXPERIMENTAL CHARACTERIZATION OF AIRCRAFT BLEED AIR PARTICULATE CONTAMINATION | 150000 | 18 | #9 | SSPC 161 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
20 | 1833 | TRP-C | MTG.ACR | ANALYTICAL LITERATURE REVIEW FOR IDENTIFICATION OF THE BASIS FOR SPECIFIED AIR CHANGE RATES (ACR) FOR INDOOR SPACES WITH MEDIUM TO HIGH ACR. - | 75000 | 9 | #1, #5 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
21 | 1837 | TRP-C | 2.1 | THE EFFECTS OF VENTILATION IN SLEEPING ENVIRONMENTS | 250000 | 30 | #2, #4 | 4.3 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
22 | 1847 | TRP | 4.2 | UPDATING CLIMATIC DESIGN INFORMATION FOR THE 2021 ASHRAE HANDBOOK, STANDARD 169, AND THE HANDBOOK OS SOKE CONTROL ENGINEERING | 150000 | 24 | #2,#5, #7 | 4.1, 5.6 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
23 | 1848 | TRP-C | MTG.IAST | ASSESSING THE IMPACTS AND VALUE OF ASHRAE's STANDARDS & TECHNOLOGY | 100000 | 12 | BOD Strategic Plan 1B | multiple | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
Work statements which have not been approved yet by RAC for Bid:
24 | 1703 | WS | 1.8 | PERFORMANCE OF VAPOR RETARDER SYSTEMS USED ON MECHANICAL INSULATION | 70000 | 12 | #1, #9 | 4.4, 10.3 | REQUIREMENT SATISFIED | JUL. 1, 2019
25 | 1716 | WS | 8.2 | EXPLORE AND QUANTIFY BEHAVIOR-DRIVEN BUILDING ENERGY USAGE | 135000 | 12 | #1, #9 | None | REQUIREMENT SATISFIED | JUL. 1, 2018
26 | 1718 | WS | 4.4 | DEVELOPMENT OF A METHOD TO DETERMINE THE MOISTURE TRANSPORT PROPERTIES THROUGH AN ASPHALT SHINGLE ROOF SYSTEM UNDER HOT AND HUMID CONDITIONS | 160000 | 24 | #1, #3, #7, #10 | None | REQUIREMENT SATISFIED | JUL. 1, 2018
27 | 1731 | WS | 8.5 | HEAT TRANSFER PERFORMANCE OF MEDIUM PRESSURE ALTERNATIVE LOWER GWP REFRIGERANTS IN A FLOODED EVAPORATOR COMPRISING AN ENHANCED TUBE BUNDLE | 225000 | 30 | #8 | None | REQUIREMENT SATISFIED | JUL. 1, 2018
28 | 1744 | WS | 4.1 | GUIDELINES FOR ACCURATE CFD MODELING OF NATURAL VENTILATION | 250000 | 24 | #7 | None | REQUIREMENT SATISFIED | OCT. 1, 2018
29 | 1748 | WS | 4.7 | ASSESS AND IMPLEMENT NATURAL AND HYBRID VENTILATION MODELS IN WHOLE-BUILDING ENERGY SIMULATIONS (PHASE 2) | 180000 | 18 | #1, #3, #7 | 4.1 | REQUIREMENT SATISFIED | OCT. 1, 2018
30 | 1763 | WS | 4.7 | DEVELOPMENT OF AN IMPROVED TOOLKIT FOR ANALYZING BUILDING ENERGY USE FROM TIMES SERIES DATA: UPDATE TO THE INVERSE MODEL TOOLKIT (RP-1050) | 160000 | 18 | #7, #1, #3 | None | REQUIREMENT SATISFIED | JUL. 1, 2019
31 | 1773 | WS | 3.1 | IGNITION POTENTIAL FROM ELECTRICAL DEVICES IN COMMERCIAL AND RESIDENTIAL APPLICATIONS USING 2L REFRIGERANTS | 150000 | 18 | #8 | None | REQUIREMENT SATISFIED | JUL. 1, 2019
32 | 1781 | WS | 7.5 | DEVELOPMENT OF A METHODOLOGY TO EVALUATE FAULT DETECTION AND DIAGNOSIS TOOLS FOR AIR HANDLING UNIT SYSTEMS | 275000 | 24 | #1 | 7.3 | REQUIREMENT SATISFIED | OCT. 1, 2019
33 | 1791 | WS | 3.1 | IMPACT OF HUMIDITY ON BURNING VELOCITY TEST CONDITIONS TO SAFELY APPLY FLAMMABLE REFRIGERANTS | 100000 | 10 | #8 | None | REQUIREMENT SATISFIED | FEB. 1, 2020
34 | 1793 | WS | 8.2 | DEVELOPMENT OF METHOD OF TEST FOR MOTOR COMPONENT THERMAL CONDUCTIVITY | 150000 | 24 | #9 | 1.11, 8.1 | REQUIREMENT SATISFIED | FEB. 1, 2020
35 | 1797 | WS | 3.1 | ASSESSMENT OF THE A/B TOXICITY CLASSIFICATION USED IN STANDARD 34 | 190000 | 18 | #8 | None | REQUIREMENT SATISFIED | JUL. 1, 2020
36 | 1804 | WS | MTG. ASEC | A GUIDELINE FOR CALCULATING THE AVOIDED SOURCE ENERGY CONSUMPTION (ASEC) DUE TO WASTE HEAT RECOVERY (WHR) TECHNOLOGIES | 200000 | 24 | #1, #3 | 7.01 MTG. BIM | REQUIREMENT SATISFIED | JUL. 1, 2020
37 | 1812 | WS | 7.5 | DETECTION AND DIAGNOSIS OF LEAKAGE FOR GROUND SOURCE HEAT PUMP SYSTEMS (GSHP) | 200000 | 24 | #1, #2, #7 | 6.8 | REQUIREMENT SATISFIED | JUL. 1, 2020
38 | 1839 | WS | 3.6 | INVESTIGATION INTO SENSIBLE TEMPERATURES FOR PORTABLE HOT WATER TEMPERATURES TO MAXIMIZEPUBLIC SAFETY, WATER AND ENERGY CONSERVATION | 85000 | 8 | #11 | EHC | REQUIREMENT SATISFIED | DEC. 1, 2021
Additional Project Funds that are likely to be Committed in February 2010 | [25 empty] | #REF! | #REF! | #REF! | #REF!
Additional Projects that could Potentially Bid in the Future - Research Topic Acceptance Request (RTAR) approved by RAC for development into a work statement:
39 | 1796 | RTAR | 8.3 | DESIGN GUIDE FOR ABSORPTION CHILLERS AND HEAT PUMPS - Accept w/ comments | 150000 | 36 | #1 | None | MAY 15, 2018 | JUL. 1, 2020
40 | 1798 | RTAR | SSPC 62.2 | IMPACT OF COMBUSTION EMISSIONS FORM GAS FIRED UNVENTED COMBUSTION DEVICES ON INDOOR AIR QUALITY | 300000 | 30 | #4 | None | MAY 15, 2018 | JUL. 1, 2020
41 | 1799 | RTAR | 5.5 | VALIDATION OF EXTRAPOLATION OF PERFORMANCE RATIGN TEST RESULTS FOR SMALL ENERGY RECOVERY EXCHANGERS TO LARGE EXCHANGERS | 200000 | 18 | #1, #2, #4, #5, #9 | None | MAY 15, 2018 | JUL. 1, 2020
42 | 1802 | RTAR | 3.1 | DEFINING THE 2 / 2L FLAMMIBILITY BOUNDARY IN STANDARD 34 | 125000 | 12 | #8 | None | MAY 15, 2018 | JUL. 1, 2020
43 | 1809 | RTAR | 7.5 | UPDATING REFERENCE GUIDE FOR DYNAMIC MODELS OF HVAC EQUIPMENT | 200000 | 24 | #1?, #10? | None | AUG. 15, 2018 | OCT. 1, 2020
44 | 1811 | RTAR | 1.5 | DETERMINING OCCUPANCY PATTERNS IN CLUSTERS OF BUILDINGS WITH DATA DRAWN FROM WEB BASED SOCIAL MEDIA | 120000 | 18 | #1, #2, #7 | None | AUG. 15, 2018 | OCT. 1, 2020
45 | 1815 | RTAR | MTG.OBB | INTEGRATING OCCUPANT BEHAVIOR DATA INTO BUILDING PERFORMANCE SIMULATION - Accept w/ comments | 120000 | 18 | #1, #2, #6, #7 | None | AUG. 15, 2019 | OCT. 1, 2021
46 | 1816 | RTAR | 9.6 | REPORTING THE ENERGY USE AND HEAT GAIN FROM IMAGIING EQUIPMENT | 200000 | 18 | #1, #7 | None | DEC. 15, 2019 | FEB. 1, 2021
47 | 1817 | RTAR | 6.8 | LONG TERM TEMPERATURE CHANGE OF GROUND HEAT EXCHANGERS | 275000 | 24 | #7, #9 | None | DEC. 15, 2019 | FEB. 1, 2021
48 | 1824 | RTAR | 8.11 | ACCOUNTING FOR BAROMETRIC PRESSURE IMPACTS ON PSYCHROMETRIC PERFORMANCE TESTING OF UNITARY AIR-CONDITIONING AND HEAT PUMP EQUIPMENT | 120000 | 18 | #5, #9 | None | MAY 15, 2019 | JUL. 1, 2021
49 | 1825 | RTAR | 5.1 | QUANTIFYING MAKEUP AIR ENTERING HOOD AND IMPACT OF SUPPLY TEMPERATURE ON HOOD PERFORMANCE - Accept w/ comments | 140000 | 12 | #10 | None | MAY 15, 2019 | JUL. 1, 2021
50 | 1827 | RTAR | 4.1 | PARTICLE INHALATION MODELING OF AIRCRAFT CABINS AS SPARSE NON-UNIFORM SPACES PHASE 1 - Accept w/ comments | 120000 | 18 | #11? | None | MAY 15, 2019 | JUL. 1, 2021
51 | 1829 | RTAR | 5.1 | INLET AND OUTLET SYSTEM EFFECTS ON MULTIPLE PLENUM FANS IN A PARALLEL ARRANGEMENT (FAN ARRAYS) FOR AIR AND SOUND PERFORMANCE - Accept w/ comments | 120000 | 18 | #1, #4 | None | MAY 15, 2019 | JUL. 1, 2021
52 | 1831 | RTAR | 10.7 | VALIDATION OF A TEST METHOD FOR APPLYING A STANDARDIZED FROST LOAD ON A TEST EVAPORATOR IN A TEST CHAMBER WITH AN OPERATING CONDITIONING SYSTEM - Accept w/ comments | 150000 | 12 | #1, #3, #7 & #9 | None | AUG. 15, 2019 | OCT. 1, 2021
53 | 1835 | RTAR | 9.1 | CHARACTERIZING THE PERFORMANCE OF ENTRAINED FLOW STACKS | 150000 | 24 | #1, #2, #5, #7, #10, #11 | None | AUG. 15, 2019 | OCT. 1, 2021
54 | 1836 | RTAR | 7.6 | DEVELOPING A STANDARDIZED CATEGORIZATION SYSTEM FOR ENERGY EFFICIENCY MEASURES | 80000 | 18 | #1, #2, #3 | None | AUG. 15, 2019 | OCT. 1, 2021
55 | 1838 | RTAR | 2.3 | INCLUSION OF ELECTRONIC AIR CLEANERS INTO ASHRAE STANDARD 145.2 - Accept w/ comments | 40000 | 6 | #7 | 2.9 SSPC 62.1 | AUG. 15, 2019 | OCT. 1, 2021
56 | 1841 | RTAR | 2.9 | ROUND ROBIN TESTING TO VALIDATE ANSI/ASHRAE STANDARD 185.2-2014 - Accept w/ comments | 75000 | 12 | #4? | None | DEC. 15, 2019 | FEB. 1, 2022
57 | 1842 | RTAR | 8.3 | DEVELIOPMENT OF COGEN/TRIGENERATION TOOLS FOR BUILDING DESIGNS | 180000 | 36 | #7 | 1.1 | DEC. 15, 2019 | FEB. 1, 2021
58 | 1843 | RTAR | 6.1 | VALIDATION OF LOW-ORDER ACOUSTIC MODELS OF COMBUSTION DRIVEN OSCILLATIONS ON RESIDENTIAL FIRE TUBE WATER HEATERS | 150000 | 18 | #1, #3, #9 | 6.6 | MAR. 15, 2020 | MAY 1, 2022
59 | 1849 | RTAR | 1.5 | DEVELOPING A FACIAL SKIN TEMPERATURE-DRIVEN THERMAL ENVIRONMENTAL CONTRIL IN THE WORKPLACE - ACCEPT W / COMMENTS | 120000 | 18 | #4, #10 | None | MAR. 15, 2020 | MAY 1, 2022
60 | 1850 | RTAR | 4.2 | EVALUATION OF ASHRAE'S DESIGN DAY PROCEDURE AGAINST RECORDED WEATHER DATA - ACCEPT W / COMMENTS | 60000 | 9 | #2, #7 | 4.1 6.5 | MAR. 15, 2020 | MAY 1, 2022
[26 empty] | #REF! | #REF! | #REF! |  | #REF!
|  |  |  | TOTAL ESTIMATED VALUE OF PROJECTS ON PLAN: | 8951000

## Returned Topics
RETURNED RESEARCH TOPIC ACCEPTANCE REQUESTS (RTARS) (These topics are NOT on the Society's Research Implementation Plan yet, but the TCs were encouraged to resubmit.)
# | TOPIC # | STATUS | RESPONSIBLE TC/TG/SSPC | TITLE | EST. COST | EST. DURATION (Months) | RESEARCH STRATEGIC PLAN GOALS SUPPORTED | CO-SPONSOR TCs | SUBMISSION HISTORY
= | = | = | = | = | = | = | = | = | =
RETURNED RTARS: Topics that were reviewed by RAC one of more times and returned with comments or requests for additional information
1 | 1706 | RTAR | 10.7 | MINIMUM REFRIGERANT CHARGE ATTAINMENT FOR COMMERCIAL REFRIGERATION SYSTEMS | 180000 | 18 | #8, #9 | None | REC. 13.06, RET. 13.06 REC.18.02, but incomplete. Need new vote and response to RAC previous comments on RTAR
2 | 1722 | RTAR | 10.7 | OPTIMIZING AIR CURTAINS FOR REFRIGERATED DISPLAY CASES WITH GLASS DOORS | 60000 | 24 | #1? | None | REC 13.10, RET 14.02 - TC working on revising RTAR based on RL's feedback (01/24/18)
3 | 1845 | RTAR | 5.1 | CONDITIONING OF REPLACEMENT AIR FOR COMMERCIAL KITCHEN HVAC | 200000 | 18 | #1, #4, #5, #7 | None | NO RTAR SUBMITTED YET BY TC. JUST NEW TRACKING # ASSIGNED. TOPIC ORIGINALLY HAD THE TRACKING NUMBER 1664, BUT IT EXPIRED FROM PLAN IN JULY 2016
REJECTED RTARS: Topics that were judged not suitable for the ASHRAE research program as presented.
1 | 1715 | RTAR | 5.1 | PRESSURE TRANSIENTS IN RAIL TUNNELS AND UNDERGROUND STATIONS | 163140 | 12 | #4 | None | REC. 13.08 REJ. 14.01
2 | 1736 | RTAR | 6.1 | A NOVEL APPROACH FOR MODELING OF HYDRONIC SYSTEMS IN BUILDING PERFORMANCE SIMULATION (BPS) TOOLS | 98000 | 12 | #1 | None | REC. 14.05 REJ. 14.06 REC. 15.08 REJ. 15.11
3 | 1737 | RTAR | 1.3 | STUDY THE EFFECTS OF MODIFYING THE WETTING SURFACES OF EVAPORATIVE CONDENSERS IN REFRIGERATION SYSTEMS FOR PERFORMANCE IMPROVEMENT | 180000 | 24 | #9 | None | REC. 14.05 REJ. 14.06
4 | 1761 | RTAR | 1.8 | MODELING HEAT AND MOISTURE TRANSPORT IN MECHANICAL INSULATION SYSTEMS ON BELOW AMBIENT INSULATED PIPES | 150000 | 24 | #1, #9 | 1.12 | REC. 15.05 REJ. 15.06
5 | 1776 | RTAR | 4.3 | CHARACTERIZING THE AIR FLOW A THE TOP OF EXHAUST STACKS FOR IMPROVED DISPERSION MODELING | 100000 | 18 | #1, #7 | None | REC. 15.10 REJ. 15.11
6 | 1777 | RTAR | 2.1 | THE EFFECTS OF OUTDOOR AIR SUPPLY RATE ON SLEEPQUALITY AND NEXT DAY PERFORMANCE | 300000 | 36 | #4 | None | REC. 15.10 REJ. 15.11
7 | 1779 | RTAR | 10.7 | RESEARCH ON THE EFFECTIVENESS OF SHELF TIP JETS IN REDUCING ENERGY COMSUMPTION OF OPEN REFRIGERATED VERTICAL DISPLAY CASES | 175000 | 30 | #1, #5, #7, #9 | None | REC. 15.12 REJ 16.01
8 | 1782 | RTAR | 7.5 | LEARNING OCCUPANCY PRESENCE IN RESIDENTIAL BUILDINGS THROUGH SMART METER DATA | 120000 | 18 | #1, #2, #7 | None | REC. 15.10 REJ. 15.11
9 | 1787 | RTAR | 9.12 | AMBIENT OUTDOOR CLIMATIC CONDITIONS AT VARIOUS HEIGHTS NEAR TALL HIGH RISE BUILDINGS | 100000 | 16 | #2, #7 | 4.2? 4.3? 4.7? | REC. 15.12 REJ 16.01
10 | 1788 | RTAR | 9.12 | CONTAMINANT VARIATION AND OUTDOOR AMBIENT QUALITY AT VARIOUS HEIGHTS NEAR TALL/HIGH RISE BUILDINGS | 150000 | 18 | #2, #7 | 4.2? 4.3? 4.7? | REC. 15.12 REJ 16.01
11 | 1803 | RTAR | EHC | THE EFFECTS OF VENTILATION AND UVGI DEVICES ON THE INFECTION OF RESPIRATORY DISEASE IN STUDENTS DORMITORIES | 200000 | 24 | #11 | None | REC 16.05 REJ 16.06
12 | 1805 | RTAR | 1.4 | NEAR OPTIMAL THERMAL ENERGY STORAGE CONTROL SEQUENCES | 350000 | 36 | #3, #4 | None | REC 16.05 REJ 16.06
13 | 1813 | RTAR | 4.7 | DEVELOPMENT OF AN ACCURACY TEST METHOD FOR RESIDENTIAL ATTIC DUCT SYSTEM SIMULATIONS IN WHOLE-BUILDING ENERGY SIMULATION PROGRAMS | 200000 | 24 | #5 | None | REC. 16.08 REJ. 16.11
14 | 1822 | RTAR | 7.6 | ALTERNATE EXPRESSIONS OF BUILDING EUI AS ENERGY PERFORMANCE METRICS | 160000 | 24 | #1, #5, #7, #10 | None | REC 17.05 REJ 17.06
15 | 1826 | RTAR | 8.4 | BIO-INSPIRED LIQUID TO AIR HEAT EXCHANGER FOR HVAC&r APPLICATIONS | 225000 | 30 | #9 | None | REC 17.05 REJ 17.06
16 | 1828 | RTAR | 4.1 | FLOW CHARACTERISTICS OF INSTALLED FLEX DUCTS | 120000 | 24 | #1 | None | REC 17.05 REJ 17.06
17 | 1832 | RTAR | 1.4 | HVAC CONTROL LOOP PERFORMANCE DIAGNOSIS | 110000 | 15 | #1, #7 | None | REC.17.08 REJ. 17.10
18 | 1834 | RTAR | MTG. OBB | EXPLORE AND QUANTIFY BEHAVIOR-DRIVEN BUILDING ENERGY USAGE | 160000 | 18 | #1, #2, #7 | None | REC.17.08 REJ. 17.10
19 | 1846 | RTAR | 2.03 | THE APPLICATION OF REAL-TIME SMALL SENSORS TO GAS CLEANING SYSTEMS FOR COMMERCIAL AND RESIDENTIAL HVAC SYSTEMS | 190000 | 18 | #1, #7 | None | REC.18.03 REJ. 18.04

## Dropped Topics
DROPPED TOPICS FROM RESEARCH IMPLEMENTATION PLAN (The following topics have been dropped from the Research Implementation Plan for various reasons.)
# | TOPIC # | STATUS | RESPONSIBLE TC/TG/SSPC | TITLE | EST. COST | EST. DURATION (Months) | RESEARCH STRATEGIC PLAN GOALS SUPPORTED | CO-SPONSOR TCs | REASON FOR DROP | 1st DRAFT OF WORK STATEMENT DUE TO RAC BY THIS DATE | RAC APPROVAL FOR BID REQUIRED BY THIS DATE OR DROPPED |  | OBJECTIVE
= | = | = | = | = | = | = | = | = | = | = | = |  | =
1 | 1368 | RTAR | 4.5 | DEVELOP LOCAL CONVECTIVE HEAT TRANSFER COEFFICIENTS FOR INDOOR AND OUTDOOR SURFACES OF FENESTRATION SYSTEMS | 135000 | 24 | A6, C6 | None | Topic time expired from plan due to lack of activity. | 2009-05-15 | JULY 2011
2 | 1425 | RTAR | 4.3 | CHARACTERIZATION OF INFILTRATION, VENTILATION AND IAQ IN MID- AND HIGH-RISE MULTI-FAMILY BUILDINGS | 185000 | 24 | A1, B2 | None |  | 2008-05-15 | JULY 2010
3 | 1426 | RTAR | 4.3 | OCCUPANT RESPONSE TO THE NOISE OF RESIDENTIAL VENTILATION FANS | 100000 | 18 | A5 | None |  | 2009-05-15 | JULY 2011
4 | 1434 | WS | 10.5 | REFRIGERATED FACILITIES DOORWAY INFILTRATION AIR ENERGY REDUCTION | 250000 | 24 | A6, A8, C6, D1, D7, E1 | None |  | REQUIREMENT SATISFIED | EXTENDED TO JUL. 1, 2013
5 | 1435 | RTAR | 10.9 | OPTIMIZING BLAST FREEZER EFFECTIVENESS | 50000 | 18 | A6, A8, C6, D1 | None |  | 2008-05-15 | JULY 2010
6 | 1445 | WS | 2.1 | ENERGY CONSERVATION, AIR-CONDITIONING AND PRODUCTIVITY IN HOT-HUMID TROPICAL REGIONS | 175000 | 36 | A2, A7, B1, B2 | EHC 2.05 5.12 7.06 |  | REQUIREMENT SATISFIED | JULY 2010
7 | 1446 | RTAR | 3.4 | PHYSICAL PROPERTIES MEASUREMENTS OF CO2 / LUBRICANT MIXTURES | 75000 | 9 | D2, D3 | None |  | 2008-05-15 | JULY 2010
8 | 1465 | RTAR | 4.1 | THE DEVELOPMENT OF A COMPUTATIONAL FLUID DYNAMICS MODEL TO REPRESENT THE PERFORMANCE OF A ROUND FLOOR (SWIRL OR INDUCTION TYPE) OUTLET USED IN UNDERFLOOR AIR DISTRIBUTION | 100000 | 18 | C1, C3 | None |  | 2008-08-15 | OCT. 2010
9 | 1479 | RTAR | 3.6 | EVALUATION OF THE IMPACT OF A MONOCHLORAMINE DISINFECTION ON LEGIONELLA COLONIZATION OF AN INSTITUTIONAL SERVICE WATER SYSTEM AND ON THE INCIDENCE OF HEALTH CARE ASSOCIATED LEGIONNAIRES' DISEASE (LD) | 25000 | 24 | B2, B3, E1, E2 | None |  | 2009-05-15 | JULY 2011
10 | 1483 | RTAR | SSPC 90.1 | STANDARD 90.1 LINKED CRITERIA SLECTION ANALYSIS BASED ON PERFORMANCE WITH DESIGN PACKAGES | 250000 | 18 | A1, A5, A6 | None |  | 2009-08-15 | OCT. 2011
11 | 1494 | RTAR | 4.2 | PROCEDURES TO GENERATE HOURLY CLIMATIC DATA FROM SPARSE DATA SETS | 75000 | 12 | A6, C1, C6, E2 | None |  | 2009-05-15 | JULY 2011 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1496 | RTAR | 4.4 | MOISTURE TRANSPORT IN CONSTRUCTION MATERIALS & ASSEMBLIES AT LOW TEMPERATURES | 190000 | 24 | A6, B2, C2 | None |  | 2009-08-15 | OCT. 2011 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1497 | RTAR | 6.1 | VENT PERFORMANCE MODEL FOR ALL CATEGORIES, MULTI-STORY AND MULTI-UNIT FOR GAS & OIL FIRED FURNANCES, BOILERS AND WATER HEATERS | 150000 | 18 | C1, C3, D1 | None |  | 2009-08-15 | OCT. 2011 | The objectives of this project are: 1. Evaluate prior vent models (such as Vent II and OHVAP) and determine the status and availability of development, test, and validation documents, computer program source codes, and current relevance and scalability to the present and future venting needs discussed above. 2. Provide a unified and user-friendly software solution that satisfies the above identified needs. This software and supporting technical report represent the primary products of this work. 3. Identify areas where testing to confirm heat and mass transfer models and criteria for acceptable designs under transient conditions are needed. This can be used to guide a Work Statement for a subsequent project. 4. Provide recommendations for modernization of the venting requirements in codes, standards and ASHRAE handbooks | [8 empty] | 75000 | 75000
14 | 1498 | WS | 6.8 | OPTIMIZED DESIGN GUIDANCE FOR OUTDOOR AIR VENTILATION OF WATER LOOP HEAT PUMP SYSTEMS | 150000 | 18 | A1, A3, A5, A6, B1, C1, E1, E2 | None |  | REQUIREMENT SATISFIED | FEB. 1, 2014
15 | 1500 | WS | 5.3 | A DESIGNER'S GUIDE FOR THE SELECTION OF AIR TERMINAL UNITS | 120000 | 24 | A1, A2, A5, A6, B2, C1, C6 | None |  | REQUIREMENT SATISFIED | OCT. 1, 2011
16 | 1502 | TRP-R | 1.4 | USER INTERFACE DESIGN FOR ADVANCED SYSTEM OPERATION | 240000 | 24 | A7, B2, C6 | 7.09 | Replaced by URP-1633 after no bids received | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED | To determine what information and system feedback the building engineering community is looking for and translate this into broad recommendations for performance specifications to support the engineering design, building operations and EMCS manufacturing communities. | [8 empty] | 90000 | 150000
17 | 1513 | RTAR | 10.3 | LIQUID/VAPOR SEPARATING VELOCITIES FOR INDUSTRIAL REFRIGERATION SYSTEMS | 100000 | 18 | D1, D2 | None | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | AUG. 15, 2010 | OCT. 2012
18 | 1514 | RTAR | 10.1 | THERMAL ENERGY RECOVERY FROM INDUSTRIAL REFRIGERATION SYSTEMS | 100000 | 12 | A7, D1, D2 | None |  | AUG. 15, 2010 | OCT. 2012
19 | 1543 | WS | 7.5 | DEMAND RESPONSE OPTIMIZATION PROTOCOL AND INTEGRATED TRAINING | 150000 | 18 | #2, #7 | None | Topic time expired from plan due to lack of activity. | REQUIREMENT SATISFIED | EXTENDED TO APR. 1, 2013
20 | 1545 | WS | 5.3 | NON-STEADY STATE OVERHEAD HEATING AND AIR CHANGE EFFECTIVENESS | 120000 | 24 | A1, B2, C6, C7, D1 | None | TC Dropped Topic | REQUIREMENT SATISFIED | JULY 2012
21 | 1548 | RTAR | 2.3 | IN-DUCT FULL-SCALE LABORATORY-EVALUATED COMPARISON OF PHOTOCATALYTIC OXIDATION (PCO) FILTERS VERSUS DRY-SCRUBBING MEDIA FILTERS | 150000 | 24 | A2, A5, B1, B3 | None | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | MAY 15, 2010 | JULY 2012
22 | 1563 | RTAR | 6.3 | IMPACT OF DUCT LEAKAGE ON INDOOR AIR QUALITY IN RESIDENTIAL SYSTEMS | 175000 | 18 | B2, B3 | None |  | AUG. 15, 2010 | OCT. 2012
23 | 1566 | WS | 8.1 | EQUATIONS TO ESTIMATE EVAPORATION RATES FROM WETTED SURFACES IN NATATORIUMS, COMMERCIAL AND INSTITUTIONAL BUILDING AND MEAT PROCESSING PLANTS | 300000 | 24 | A1, A6, A7, B2, C1, D1 | 1.12 8.12 |  | REQUIREMENT SATISFIED | EXTENDED TO JUL. 1, 2014
24 | 1573 | WS | 9.1 | DETERMINATION OF SUITABLE REPLACEMENT FOR SF6 WHEN USED AS A TRACER GAS IN ACCORDANCE WITH ASHRAE METHODS OF TEST 110 AND 129 | 125000 | 12 | #9, #8 | None |  | MAY 15, 2015 | JULY 2017
25 | 1576 | WS | 6.9 | TES SYSTEM PERFORMANCE METRICS RELATED TO CARBON EMISSION REDUCTIONS AT THE POWER GENERATION SOURCE | 100000 | 18 | A6 | 1.1 |  | REQUIREMENT SATISFIED | FEB. 1, 2013
26 | 1577 | RTAR | 8.4 | TUBE-TO-TUBE CONDUCTION EFFECTS IN FINNED TUBE HEAT EXCHANGERS | 200000 | 24 | C1, D2, D1, A1, A6, A7 | None |  | DEC. 15, 2010 | FEB. 2013
27 | 1610 | WS | 4.2 | DEVELOPMENT OF A TRANSPOSITION MODEL FOR CLEAR-SKY SOLAR IRRADIANCE | 35000 | 12 | A6, B2, C1, C6, D1 | 4.01 4.05 |  | REQUIREMENT SATISFIED | FEB. 1, 2014
28 | 1618 | WS | 9.6 | LITERATURE SEARCH AND RISK ASSESSMENT FOR ESTABLISHING A LOW LIMIT OF RELATIVE HUMIDITY LEVELS IN HEALTH CARE SPACES | 50000 | 6 | A1, A6 | None |  | DEC. 15, 2010 | FEB. 2013
29 | 1619 | RTAR | 9.9 | DATA CENTER GASEOUS CONTAMINATION LIMITS AND MEANS OF MONITORING | 180000 | 18 | A1, A5, D7, E1, E2 | None |  | DEC. 15, 2012 | FEB. 1, 2015
30 | 1623 | RTAR | 5.3 | DEVELOP A METHOD FOR TESTING THE MIST REMOVAL EFFICIENCY AND AIR FLOW RESISTANCE OF OIL MIST COLLECTORS | 150000 | 24 | #9, A1 | None
31 | 1626 | RTAR | 2.4 | ENERGY IMPLICATIONS OF AIR FILTRATION IN COMMERCIAL BUILDINGS | 250000 | 24 | #2, #5, #7 | None | RL Dropped Topic
32 | 1628 | RTAR | 3.4 | PHYSICAL PROPERTIES MEASUREMENTS OF HFO-1234yf / LUBRICANT MIXTURES | 100000 | 12 | #8, #9, D2, D3, D6 | None |  | AUG. 15, 2012 | OCT. 1, 2014
33 | 1635 | RTAR | 4.3 | SIMPLIFIED PROCEDURE FOR CALCULATING EXHAUST/INTAKE SEPARATION DINSTANCES | 50000 | 12 | #9, #10 | None |  | DEC. 15, 2012 | FEB. 1, 2015
34 | 1639 | RTAR | 1.4 | COMPARATIVE LAB AND FIELD EVALUATION OF BUILDING PRESSURE CONTROL METHODS | 199000 | 36 | #1, #2, #7, #9, #11 | SSPC 62.1 |  | AUG. 15, 2013 | OCT. 1, 2015
35 | 1653 | RTAR | 2.9 | QUANTIFY THE DEGRADATION OF CRITICAL HVAC COMPONENTS AND MATERIALS EXPOSED TO UVC LEVELS TYPICALLY USED IN HVAC SYSTEMS. | 75000 | 18 | #9, #4, #1 |  |  | AUG. 15, 2014 | OCT. 1, 2016
36 | 1657 | RTAR | EHC | EFFECTIVE VENTILATION SYSTEMS FOR AIRBORNE INFECTION ISOLATION ROOMS TO REDUCE POTENTIAL CROSS INFECTION | 250000 | 36 | #11 |  |  | AUG. 15, 2015 | OCT. 1, 2017
37 | 1664 | WS | 5.1 | CONDITIONING OF REPLACEMENT AIR FOR COMMERCIAL KITCHEN HVAC | 150000 | 18 | #1, #4, #5, #7 | None |  | MAY 15, 2014 | JUL. 1, 2016
38 | 1666 | RTAR | 5.3 | EXPERIMENTAL EVALUATION OF THE THERMAL AND VENTILATION PERFORMANCE OF STRATIFIED AIRE DISTRIBUION SYSTEMS COUPLED WITH PASSIVE CHILLED BEAMS | 195000 | 24 | #1, #2, #5, #7 | 4.07 |  | MAY 15, 2014 | JUL. 1, 2016
39 | 1680 | RTAR | 6.8 | INVESTIGATION OF THE ENVIRONMENTAL IMPACTS OF GROUND SOURCE HEAT PUMPS - DROPPED BY TC PER A14 RL REPORT | 75000 | 18 | #1, #3, #9 |  | TC Dropped Topic
40 | 1684 | RTAR | 9.1 | DISPERSION OF REFRIGERANT RELEASES TO CONNECTING SPACES VIA TRANSFER OPENINGS | 85000 | 15 | #1, #9 | SSPC 15 8.07 | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | MAY 15, 2015 | OCT.1, 2016
41 | 1685 | RTAR | 2.9 | FIELD STUDIES TO IDENTIFY THE BIOFILM MICRO-ORGANISIMS ON HVAC COOLING COILS AND IN DRAIN PANS. - DROPPED BY TC PER W15 RL REPORT |  |  |  |  | TC Dropped Topic
42 | 1690 | WS | 5.9 | INTERACTION OF TUNNEL VENTILATION PERFROMANCE WITH FIXED FIRE SUPPRESSION | 145000 | 15 | #7 | 5.06 | TC Dropped Topic FHWA will lead project instead | MAY 15, 2015 | JUL. 1, 2017
43 | 1697 | RTAR | 7.5 | REDUCE SIMULTANEOUS HEATING AND COOLING IN COMMERCIAL BUILDINGS | 150000 | 18 | #1, #7 | None | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | MAY 15, 2015 | JUL. 1, 2017
44 | 1700 | RTAR | 4.2 | A GLOBAL DATABASE OF MOISTURE DESIGN REFERENCE YEARS FOR HYGROTHERMAL ANALYSIS AND DESIGN OF BUILDINGS | 150000 | 24 | #1, #5, #7, #10 | None |  | MAY 15, 2015 | JULY 2017
45 | 1707 | RTAR | 2.6 | ANNOYANCE THRESHOLD OF TONES IN NOISE AS RELATED TO BUILDING SERVICES EQUIPMENT | 180000 | 24 | #4 | None | Topic time expired from display on plan due to no WS draft. | MAY 15, 2015 | JULY 2017
46 | 1739 | WS | 9.9 | DEVELOPMENT OF IMPROVED AND INTEGRATED ENERGY MODELING SOFTWARE FOR DATA CENTERS | 234250 | 18 | #2, #5 | None | WS DROPPED BY RAC DUE TO NO TC ACTIVITY IN 2 YEARS | NOT ON PLAN - RTAR STAGE SKIPPED
47 | 1749 | WS | 1.5 | A BIM AND PHYSICS-BASED MODELING ENABLED PLATFORM FOR MONITORING AND VISUALIZING HIGH PERFORMANCE COMMERCIAL BUILDINGS | 200000 | 24 | #1, #6 | 7.3?
48 | 1750 | RTAR | 1.5 | DEVELOPMENT OF REFERENCE EQUIPMENT MODEL FOR STANDARDIZATION OF VIRTUAL EQUIPMENT AND DEVICE CREATION (BIM FOR HVAC EQUIPMENT) | 150000 | 18 | #7 | 4.7 | TC Dropped Topics
49 | 1751 | RTAR | 1.5 | HVAC SYSTEM THERMAL CONTROL AND ENERGY PERFORMANCE USING WORK AND DATA EXCHANGE PROCESSES | 180000 | 18 | #7 | 1.4
50 | 1758 | WS | 5.2 | CFD MODELING AND LABORATORY TESTING OF FLAT OVAL DIVERGING FLOW TEES TO DETERMINE LOSS COEFFICIENTS | 165000 | 24 | #1, #7 | None | WS DROPPED BY RAC DUE TO NO TC ACTIVITY IN 2 YEARS | NOT ON PLAN - RTAR STAGE SKIPPED
51 | 1795 | RTAR | 9.11 | NEW TECHNIQUE DEVELOPMENT OF USING ROOM AIRFLOW CONTROL DEVICES TO ESTIMATE ROOM ENCLOSURE AIR-TIGHTNESS IN CONTROLLED ENVIRONMENTS | 200000 | 24 | #1?, #11?, #4? | None | TC Dropped Topic | NOT ON PLAN - RTAR STAGE SKIPPED