## Goals
R E S E A R C H 2 0 0 5 - 2 0 1 0 S T R A T E G I C T H E M E S & G O A L S | R E S E A R C H 2 0 1 0 - 2 0 1 5 S T R A T E G I C T H E M E S & G O A L S
A. ENERGY & RESOURCES THEME | GOAL #
STRATEGIC GOALS: | 1 | Maximize the actual operational energy performance of buildings and facilities
A1. Provide guidance on techniques and move 30% towards net zero-energy use bldgs by 2008, 50% by 2012, and 70% by 2015
A2. Produce by 2015 new residential and light commercial bldgs that use 70% less energy based on ASHRAE 90.2-2001 | 2 | Progress toward Advanced Energy Design Guide (AEDG) and cost-effective net-zero-energy (NZE) buildings
A3. Develop by 2015 economically viable applications of renewable energy that reduce conventional energy usage by 25%
A4. Develop systems and components that reduce energy use in supermarkets by 30% by 2015 | 3 | To reduce significantly the energy consumption for HVAC&R, water heating and lighting in existing homes.
A5. Optimize & make consistent ASHRAE standards 90, 62, AND 55 for energy efficiency & IEQ for indoor built environments
A6. Develop integrated best practices design methods that optimize energy eff., life cycle cost, IEQ, and environmental impact | 4 | Significantly advance our understanding of the impact of indoor environmental quality (IEQ) on work performance, health symptoms and perceived
A7. Develop methods for measured bldg.(energy, cost, emissions) & occupant (comfort, health, productivity) performance. |  | environmental quality in offices, providing a basis for improvements in ASHRAE standards, guidelines, HVAC&R designs and operation practices.
A8. Establish benchmark data on energy use in industrial refrigeration
| 5 | Support the development of ASHRAE energy standards and reduce effort required to demonstrate compliance
B. INDOOR ENVIRONMENTAL QUALITY THEME
STRATEGIC GOALS: | 6 | Building Information Modeling (BIM) of energy efficient, high-performing buildings
B1. Make improvements in occupant health and comfort that yield 20% increase in productivity by 2015
B2. Provide optimal indoor environment for bldgs, vehicles, & facilities with respect to comfort, productivity, health, & safety | 7 | Support development of tools, procedures and methods suitable for designing low energy buildings
B3. Understand better how contagious viruses are transmitted in indoor environments and develop countermeasures
B4. Develop self-diagnostic inspection methods for HVAC systems that minimize impacts on comfort, health, & productivity | 8 | Facilitate use of natural and low global warming potential (GWP) synthetic refrigerants and seek methods to reduce refrigerant charge
C. TOOLS AND APPLICATIONS THEME | 9 | Support the development of improved HVAC&R components ranging from residential through commercial to provide improved system efficiency ,
STRATEGIC GOALS: |  | affordability, reliability and safety
C1. Develop more effective tools that will improve the productivity of the design process by 25% by 2015
C2. Develop dual path standards where paths are a) Prescriptive based, and b) Performance based | 10 | Significantly increase the understanding of energy efficiency , environmental quality and the design of buildings in engineering and architectural education
C3. Develop methods to allow a designer to accurately model a bldg in virtual reality in no more than 1 week by 2010
C4. Develop a measurement-based rating system to establish the environmental performance of a bldg & its systems | 11 | Understand influences of HVAC&R on airborne pathogen transmission in public spaces and develop effective control strategies
C5. Develop self-calibrating & low-cost sensor systems that measure control variables (comfort, health, productivity)
C6. Establish design tools to improve the installed energy eff. of HVAC&R systems and components
C7. Provide design guidance for bldgs. and systems to address the past and expected change in climatic conditions
D. EQUIPMENT, COMPONENTS & MATERIALS THEME
STRATEGIC GOALS:
D1. Establish techniques to improve energy eff. & reliability of HVAC&R components
D2. Continue research into new alternative and natural refrigerants
D3. Improve performance and reliability and minimize the environmental impacts of working fluids and materials
D4. Advance ASHRAE's role in the safety and security of food distribution
D5. Develop reliable, durable, and self-correcting sensor technology for monitoring IEQ, pollutants, energy conservation, & FDD
D6. Move one or more non-traditional technologies to market readiness by 2010
D7. Develop techniques that reduce the installed energy use of HVAC&R system auxiliary equipment 50% by 2015
E. EDUCATION & OUTREACH THEME
STRATEGIC GOALS:
E1. Make the results of ASHRAE research available to the technical committee
E2. Ensure that ASHRAE research has an international impact

## Current Plan
| A S H R A E R E S E A R C H I M P L E M E N T A T I O N P L A N |  |  |  |  | Winter 2020
# | TOPIC # | STATUS | RESPONSIBLE TC/TG | TITLE | EST. COST | EST. DURATION (Months) | RESEARCH STRATEGIC PLAN GOALS SUPPORTED | CO-SPONSOR TCs | 1st DRAFT OF WORK STATEMENT DUE TO RAC BY THIS DATE | RAC APPROVAL FOR BID REQUIRED BY THIS DATE OR DROPPED | DATE OF LAST SUBMISSION (YR.MO) | OBJECTIVE | Proposed Rating: None Low Medium Med.-High High | 0 pts 45 pts 135 pts 270 pts 405 pts | Rating: None: Low: Medium: High: | 0 pts 10 pts 30 pts 90 pts | Rating: None: e.g. missing info. Low: e.g. limited use & small improvement Medium: e.g. large use or large improvement High: e.g. large use and large improvement | 0 pts 15 pts 45 pts 135 pts | Rating: None: Low: Medium: High: | 0 pts 10 pts 30 pts 90 pts | Rating: None: Low: Medium: High: | 0 pts 15 pts 45 pts 135 pts | Rating: None or no support Low: Medium: Support High: Great Project! | 0 pts 5 pts 15 pts 45 pts | Total Score | FY 09-10 Draft Budget $2,913,200 | FY 10-11 Draft Budget TBD | FY 11-12 Draft Budget TBD | FY 12-13 Draft Budget TBD | FY 08-09 Budget $2,668,000
= | = | = | = | = | = | = | = | = | = | = | = |  | = | = | = | = | = | = | = | = | = | = | = | = | = | = |  | = |  | =
Research Project Funds Already Committed as of 1/1/10 | [25 empty] | 1689117 | 916712 | 216250 | 0 | 2504352
Additional Project Funds that could be Potentially Committed by April 2010 | [25 empty] | #REF! | #REF! | #REF! | #REF!
Solicited Research Projects That Could Potentially be Funded by annual 2020 Based upon Bids Received in winter 2020 or earlier:
| 1799 | TRP | 5.5 | VALIDATION OF EXTRAPOLATION OF PERFORMANCE RATING TEST RESULTS FOR SMALL ENERGY EXCHANGERS TO LARGE EXCHANGERS - RAC Letter ballot closes Monday 3/2 | 190499 | 22 | #1, #2, #4, #5, #9 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1817 | TRP | 6.8 | LONG TERM TEMPERATURE CHANGE OF GROUND HEAT EXCHANGERS - RAC Letter ballot closes Monday 3/2 | 160000 | 20 | #7, #9, | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1830 | TRP | 9.3 | EXPERIMENTAL CHARACTERIZATION OF AIRCRAFT BLEED AIR PARTICULATE CONTAMINATION - RAC Letter ballot closes Monday 3/2 | 150000 | 18 | #9 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1865 | TRP | 1.4 8.10 | OPTIMIZING SUPPLY AIR TEMPERATURE CONTROL FOR DEDICATED OUTDOOR AIR SYSTEMS - Not awarded. Rebid or award to lowest cost responsive bid | 180000 | 24 | #1, #2, #7, #9 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
Research Projects That Could Potentially Bid in the spring 2020 - Rebids, Approved, and Conditionally Approved TRPs:
| 1566 | TRP-C | 8.10 9.8 | EQUATIONS TO ESTIMATE EVAPORATION RATES FROM HEATED WATER POOLS IN INDOOR RECREATIONAL AQUATIC FACILITIES | 150000 | 24 | #1, #5, #7, #10 | 9.8 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1703 | TRP-C | 1.8 10.3 4.4 | PERFORMANCE OF VAPOR RETARDER SYSTEMS USED ON MECHANICAL INSULATION | 70000 | 12 | #4 | 2.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1716 | TRP-C | 8.2 | OIL CONCENTRATION OF FIELD-INSTALLED LIQUID CHILLERS WITH FLOODED TYPE EVAPORATORS | 135000 | 24 | #1, #9 | NONE | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1718 | TRP-C | 4.4 SSPC 160 1.12 | DEVELOPMENT OF A METHOD TO DETERMINE THE MOISTURE TRANSPORT THROUGH A ROOF SHINGLE SYSTEM UNDER REAL CONDITIONS | 160000 | 24 | #1, #3, #7, #10 | 1.12 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1740 | TRP-R | 3.3 | HYDROGEN FLUORIDE CAPACITY OF DESICCANTS | 120000 | 9 | D1 | 3.2 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1789 | TRP-R | 4.5 | OPTICAL AND THERMAL PERFORMANCE OF HOLLOW GLASS BLOCKS | 197000 | 18 | #1, #7 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1790 | TRP-R | 3.3 | DISTRIBUTION OF WATER BETWEEN VAPOR AND LIQUID PHASES OF LOW GWP REFRIGERANTS | 100000 | 12 | #8? | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1797 | TRP-C | 3.1 | ASSESSMENT OF THE A/B TOXICITY CLASSIFICATION USED IN STANDARD 34 | 75000 | 10 | #8 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1831 | TRP-C | 10,7 | VALIDATION OF A TEST METHOD FOR APPLYING A STANDARDIZED FROST LOAD ON A TEST EVAPORATOR IN A TEST CHAMBER WITH AN OPERATING CONDITIONING SYSTEM - Accept w/ comments | 75000 | 10 | #8 | None | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1835 | TRP | 9.1 | CHARACTERIZING THE PERFORMANCE OF ENTRAINED FLOW STACKS | 245000 | 30 | #1, #2, #5, #7, #10, #11 | 4.3 5.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1850 | TRP-C | 4.2 | EVALUATION OF ASHRAE'S DESIGN DAY PROCEDURE AGAINST RECORDED WEATHER DATA | 60000 | 9 | #2, #7 | 4.1 6.5 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
| 1879 | TRP-C | 3.4 | FOAMABILITY PROPERTIES OF LGWP REFRIGERANT AND OIL MIXTURES | 100000 | 12 | #8, #9 | 8.1 | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED
Work statements which have not been approved yet by RAC for Bid:
| 1822 | WS | 7.6 | ALTERNATE EXPRESSIONS OF BUILDING EUI AS ENERGY PERFORMANCE METRICS - Accept w/ comments | 150000 | 24 | #1, #5, #7, #10 | None | DEC. 15, 2021 | FEB. 1, 2023
| 1841 | WS | 2.9 | ROUND ROBIN TESTING TO VALIDATE ANSI/ASHRAE STANDARD 185.2-2014 - Accept w/ comments | 75000 | 12 | #4? | None | DEC. 15, 2020 | FEB. 1, 2022
| 1842 | WS | 8.3 | DEVELIOPMENT OF COGEN/TRIGENERATION TOOLS FOR BUILDING DESIGNS | 180000 | 36 | #7 | 1.1 | DEC. 15, 2020 | FEB. 1, 2022
| 1843 | WS | 6.1 | VALIDATION OF LOW-ORDER ACOUSTIC MODELS OF COMBUSTION DRIVEN OSCILLATIONS ON FIRE TUBE WATER HEATERS. | 150000 | 18 | #1, #3, #9 | 6.06 | MAR. 15, 2020 | MAY. 1, 2022
| 1849 | WS | 1.5 | DEVELOPING A FACIAL SKIN TEMPERATURE-DRIVEN THERMAL ENVIRONMENTAL CONTRIL IN THE WORKPLACE - Accept w/ comments - TC Dropped in KC | 120000 | 18 | #8 | None | MAR. 15, 2020 | MAY. 1, 2022
| 1851 | WS | 3.1 | DIELECTRIC PROPERTIES OF LOWER GWP REFRIGERANTS | 100000 | 6 | #1 | 9.6 SSPC 62.1 | MAY. 15, 2020 | JUL. 1, 2022
| 1854 | WS | 2.9 | DATABASE OF ULTRAVIOLET INACTIVATION RATE CONSTANT (K-VALUES) FOR MICROOGANISMS CRITICAL TO SYSTEM DESIGN - Accepted | 50000 | 24 | #1 | 7.3 | MAY. 15, 2021 | JUL. 1, 2023
| 1856 | WS | 3.3 | MOSITURE TOLERANCE AND EFFECTS IN CO2 REFRIGERATION SYSTEMS- Accept w/ comments | 120000 | 24 | #8 | 10.1 | AUG. 15, 2021 | OCT. 1, 2023
| 1857 | WS | 4.7 | IMPROVED SIMPLIFIED METHODOLOGY FOR DESCRIBING AND CALCULATING HEAT CONDUCTION BETWEEN BUILDINGS AND THE GROUND. - Accept w/ comments | 75000 | 10 | #8 | None | AUG. 15, 2020 | OCT. 1, 2022
| 1858 | WS | 2.3 | EVALUATION OF HVAC VENTILATION EFFECTIVENESS IN REDUCING SEMI-VOLATILE ORGANIC COMPOUNDS (SVOCs) IN INDOOR SPACES - Accept w/ comments | 199000 | 6 | #7, #8 | None | AUG. 15, 2021 | OCT. 1, 2023
| 1859 | WS | 2.8 | RESIDENTIAL WATER FIXTURE USE SCHEDULES BASED ON MEASURED OCCUPANT BEHAVIOR - Accept w/ comments | 150000 | 18 | #8 | None | AUG. 15, 2020 | OCT. 1, 2022
| 1861 | WS | 2.1 | US / CANADIAN RESIDENCES: INDOOR CONDITIONS, THERMAL COMFORT, OCCUPANT BEHAVIOUR AND ENERGY DEMAND - Accept w/ comments | 200000 | 24 | #1, #3 | 7.01 MTG. BIM | AUG. 15, 2020 | OCT. 1, 2022
| 1862 | WS | 1.8 | DETERMINING THE IMPACT OF SEALING HOT INSULATION SYSTEM METAL JACKETING JOINTS ON WATER INTRUSION AND RETENTION IN THE SYSTEM - - Accept w/ comments | 100000 | 18 | #9 | SSPC 161 | AUG. 15, 2020 | OCT. 1, 2022
| 1864 | WS | SSPC 170 | INVESTIGATING THE APPLICABILITY OF STANDARD 62.1's VENTILATION RATE PROCEDURE FOR HEALTHCARE ROOMS - Accept w/ comments | 125000 | 36 | #2, #4 | 9.06 SSPC 62.1 | AUG. 15, 2020 | OCT. 1, 2022
| 1866 | WS | 3.8 | ASSESS REFRIGERANT DETECTOR CHARACTERISTICS FOR USE IN HVACR EQUIPMENT- Accepted As-Is | 85000 | 8 | #11 | EHC | AUG. 15, 2020 | OCT. 1, 2022
Additional Project Funds that are likely to be Committed in February 2010 | [25 empty] | #REF! | #REF! | #REF! | #REF!
Additional Projects that could Potentially Bid in the Future - Research Topic Acceptance Request (RTAR) approved by RAC for development into a work statement:
| 1868 | RTAR | SSPC 62.1 2.08 4.10 | FEASIBILITY OF PREDICTING INDOOR FORMALDEHYDE, VOC, AND CO2 CONCENTRATIONS USING SIMPLIFIED INPUTS TO AIR QUALITY MODELS IN NEW OFFICE BUILDINGS - Accept w/ comments | 150000 | 24 | #1, #5, #7, #10 | None | AUG. 15, 2020 | OCT. 1, 2022 | #VALUE! | 2019-01-12 | 2020-02-27 | 411
| 1869 | RTAR | 2.03 | EVALUATION OF INDOOR AIR CONTAMINANTS WITH RESPECT TO DEVELOPMENT OF A REVISED INDOOR AIR QUALITY PROCEDURE (IAQP) DESIGN COMPOUND AND DESIGN TARGET LISTS FOR STANDARD 62.1 - Accept w/ comments | 150000 | 18 | #1, #3, #9 | 6.06 | AUG. 15, 2020 | OCT. 1, 2022 | #VALUE! | 2018-04-18 | 2020-02-27 | 680
| 1871 | RTAR | 1.08 10.03 | HYROTHERMAL MODELING OF BELOW AMBIENT PIPE INSULATION SYSTEMS IN BOTH BUILDINGS AND REFRIGERATION - Accept w/ comments | 120000 | 18 | #4, #10 | None | DEC. 15, 2020 | FEB. 1, 2023 | #VALUE! | 2018-04-18 | 2020-02-27 | 680
| 1872 | RTAR | 7.06 | UPDATING SITE ENERGY TRAGETS FOR ASHRAE STANDARD 100-2018 - ENERGY EFFICIENCY IN EXISTING BUILDINGS - Accept w/ comments | 100000 | 12 | #8, #9 | None | DEC. 15, 2020 | FEB. 1, 2023 | #VALUE! | 2018-06-23 | 2020-02-27 | 614
| 1873 | RTAR | 2.09 | UPPER-AIR ULTRAVIOLET GERMICIDAL IRRADIATION (UVGI) FOR TALL SPACES - Accept w/ comments | 75000 | 12 | #1, #4 #11 | 9.06 | DEC. 15, 2020 | FEB. 1, 2023 | #VALUE! | 2019-06-26 | 2020-02-27 | 246
| 1874 | RTAR | 4.02 | CLIMATIC DESIGN FOR ROOF TOP HVAC EQUIPMENT - Accept w/ comments | 75000 | 8 | #8, #9 | 10.06 | DEC. 15, 2020 | FEB. 1, 2023 | #VALUE! | 2019-10-30 | 2020-02-27 | 120
| 1878 | RTAR | 4.03 2.04 SSPC 62.1 | OUTDOOR PARTICULATE MATTER PENETRATION AND INDOOR PM REMOVAL RATES IN NATURALLY VENTILATED COMMERCIAL BUILDINGS - Accept w/ comments | 250000 | 18 | #1, #2, #5, #7 | None | MAR. 15, 2021 | MAY. 1, 2023 | #VALUE! | 2018-11-01 | 2020-02-27 | 483
| 1882 | RTAR | 5.03 2.06 | PROCEDURE FOR ESTIMATING OCCUPIED SPACE SOUND LEVELS IN THE APPLICATION OF UFAD AIR TERMINALS AND AIR OUTLETS- Accept w/ comments | 200000 | 24 | #1, #4, #7 | None | MAY. 15, 2021 | JUL. 1, 2023 | #VALUE! | 2019-10-30 | 2020-02-27 | 120
| 1884 | RTAR | 3.01 | THE INCORPORATION OF ODORANTS IN REFRIGERANTS TO IMPROVE LEAK DETECTION--PHASE II, EXPERIMENTAL STUDY. Accept-as-is | 205000 | 18 | #2, #5, #7 | MTG.OBB | DEC. 15, 2021 | FEB. 1, 2023 | #VALUE! | 2018-11-01 | 2020-02-27 | 483
| 1885 | RTAR | 6.07 1.09 | SOLAR PV DESIGN GUIDE FOR THE BUILDING PROFESSIONAL INCLUDING HVAC AND BUILDING INTERACTIONS - Accept w/ comments | 150000 | 34 | #3, #7, #9 | 7.06 RBC | AUG. 15, 2021 | OCT. 1 ,2023 | #VALUE! | 2018-11-01 | 2020-02-27 | 483
| 1886 | RTAR | 3.02 | KINETIC AND MECHANISTIC STUDY OF THE BREAKDOWN AND INTERACTIONS OF HFO REFRIGERANTS - Accept as-is | 100000 | 12 | #9 | 10.03 | AUG. 15, 2021 | OCT. 1 ,2023 | #VALUE! | 2018-11-01 | 2020-02-27 | 483
| 1887 | RTAR | 2.02 | ENERGY USE IN INDOOR PLANT ENVIRONMENTS - Accept w/ comments | 50000 | 18 | #11 | 9.06 | AUG. 15, 2021 | OCT. 1 ,2023 | #VALUE! | 2018-11-01 | 2020-02-27 | 483
| 1888 | RTAR | 7.04 | MAXIMIZING EFFICIENCY OF ENERGY CONVERSION TECHNOLOGIES OF BUILDINGS VIA EXERGY-BASED ANALYSIS - - Accept w/ comments | 150000 | 24 | #8 | 3.08 | AUG. 15, 2021 | OCT. 1 ,2023 | #VALUE! | 2018-11-01 | 2020-02-27 | 483
| 1889 | RTAR | 9.06 | GRAYWATER USE IN HEALTHCARE FACILITIES; DETERMINING RISK AND APPROPRIATE DESIGN RESPONSES - Accept w/ comments | 50000 | 12 | #11? | None | AUG. 15, 2021 | OCT. 1 ,2023
| 1890 | RTAR | 6.08 | MINIMUM FLOW VELOCITIES FOR PURGING AIR AND DEBRIS FROM HYDRONIC PIPING SYSTEMS - Accept w/ comments | 150000 | 18 | #1, #4 | None | AUG. 15, 2021 | OCT. 1 ,2023
| 1891 | RTAR | 3.04 | ASSESSMENT OF TRIBOLOGICAL INTERACTIONS OF REFRIGERANTS AND LUBRICANTS IN HVAC SYSTEMS - Accept w/ comments | 40000 | 9 | #1, #3, #7 & #9 | None | DEC. 15, 2021 | FEB. 1, 2023
TOPICS REMOVED FROM DISPLAY AFTER 2 YEARS ON PLAN WITH NO WORKSTATEMENT SUBMITTED
[26 empty] | #REF! | #REF! | #REF! |  | #REF!
|  |  |  | TOTAL ESTIMATED VALUE OF PROJECTS ON PLAN: | 5381000

## Returned Topics
RETURNED RESEARCH TOPIC ACCEPTANCE REQUESTS (RTARS) (These topics are NOT on the Society's Research Implementation Plan yet, but the TCs were encouraged to resubmit.)
# | TOPIC # | STATUS | RESPONSIBLE TC/TG/SSPC | TITLE | EST. COST | EST. DURATION (Months) | RESEARCH STRATEGIC PLAN GOALS SUPPORTED | CO-SPONSOR TCs | SUBMISSION HISTORY
= | = | = | = | = | = | = | = | = | =
RETURNED RTARS: Topics that were reviewed by RAC one of more times and returned with comments or requests for additional information
1 | 1722 | RTAR | 10.7 | OPTIMIZING AIR CURTAINS FOR REFRIGERATED DISPLAY CASES WITH GLASS DOORS | 60000 | 24 | #1? | None | REC 13.10, RET 14.02
2 | 1750 | RTAR | 1.5 | DEVELOPMENT OF REFERENCE EQUIPMENT MODEL FOR STANDARDIZATION OF VIRTUAL EQUIPMENT AND DEVICE CREATION (BIM for HVAC EQUIPMENT) | 150000 | 18 | #7? | 4.7 | REC.14.08, RET. 14.10
3 | 1751 | RTAR | 1.5 | HVAC SYSTEM THERMAL CONTROL AND ENERGY PERFORMANCE USING WORK AND DATA EXCHANGE PROCESSES | 180000 | 18 | #7? | 1.4 | REC.14.08, RET. 14.10
4 | 1795 | RTAR | 9.11 | NEW TECHNIQUE DEVELOPMENT OF USING ROOM AIRFLOW CONTROL DEVICES TO ESTIMATE ROOM ENCLOSURE AIR-TIGHTNESS IN CONTROLLED ENVIRONMENTS | 200000 | 24 | #1?, #11?, #4? | None | REC. 16.08 - Need TC Vote
5 | 1843 | RTAR | 6.1 | VALIDATION OF LOW-ORDER ACOUSTIC MODELS OF COMBUSTION DRIVEN OSCILLATIONS ON RESIDENTIAL FIRE TUBE WATER HEATERS | 99000 | 18 | ? | None | REC. 17.12 - Need TC Vote
6 | 1845 | RTAR | 5.1 | CONDITIONING OF REPLACEMENT AIR FOR COMMERCIAL KITCHEN HVAC | 200000 | 18 | #1, #4, #5, #7 | None | TOPIC ORIGINALLY HAD THE TRACKING NUMBER 1664, BUT IT EXPIRED FROM PLAN IN JULY 2016
REJECTED RTARS: Topics that were judged not suitable for the ASHRAE research program as presented.
1 | 1706 | RTAR | 10.7 | MINIMUM REFRIGERANT CHARGE ATTAINMENT FOR COMMERCIAL REFRIGERATION SYSTEMS | 180000 | 18 | #8, #9 | None | REC. 13.06, RET. 13.06 REC.18.07 REJECT 18.10
2 | 1736 | RTAR | 6.1 | A NOVEL APPROACH FOR MODELING OF HYDRONIC SYSTEMS IN BUILDING PERFORMANCE SIMULATION (BPS) TOOLS | 98000 | 12 | #1 | None | REC. 14.05 REJ. 14.06 REC. 15.08 REJ. 15.11
3 | 1737 | RTAR | 1.3 | STUDY THE EFFECTS OF MODIFYING THE WETTING SURFACES OF EVAPORATIVE CONDENSERS IN REFRIGERATION SYSTEMS FOR PERFORMANCE IMPROVEMENT | 180000 | 24 | #9 | None | REC. 14.05 REJ. 14.06
4 | 1761 | RTAR | 1.8 | MODELING HEAT AND MOISTURE TRANSPORT IN MECHANICAL INSULATION SYSTEMS ON BELOW AMBIENT INSULATED PIPES | 150000 | 24 | #1, #9 | 1.12 | REC. 15.05 REJ. 15.06
5 | 1776 | RTAR | 4.3 | CHARACTERIZING THE AIR FLOW A THE TOP OF EXHAUST STACKS FOR IMPROVED DISPERSION MODELING | 100000 | 18 | #1, #7 | None | REC. 15.10 REJ. 15.11
6 | 1777 | RTAR | 2.1 | THE EFFECTS OF OUTDOOR AIR SUPPLY RATE ON SLEEPQUALITY AND NEXT DAY PERFORMANCE | 300000 | 36 | #4 | None | REC. 15.10 REJ. 15.11
7 | 1779 | RTAR | 10.7 | RESEARCH ON THE EFFECTIVENESS OF SHELF TIP JETS IN REDUCING ENERGY COMSUMPTION OF OPEN REFRIGERATED VERTICAL DISPLAY CASES | 175000 | 30 | #1, #5, #7, #9 | None | REC. 15.12 REJ 16.01
8 | 1782 | RTAR | 7.5 | LEARNING OCCUPANCY PRESENCE IN RESIDENTIAL BUILDINGS THROUGH SMART METER DATA | 120000 | 18 | #1, #2, #7 | None | REC. 15.10 REJ. 15.11
9 | 1787 | RTAR | 9.12 | AMBIENT OUTDOOR CLIMATIC CONDITIONS AT VARIOUS HEIGHTS NEAR TALL HIGH RISE BUILDINGS | 100000 | 16 | #2, #7 | 4.2? 4.3? 4.7? | REC. 15.12 REJ 16.01
10 | 1788 | RTAR | 9.12 | CONTAMINANT VARIATION AND OUTDOOR AMBIENT QUALITY AT VARIOUS HEIGHTS NEAR TALL/HIGH RISE BUILDINGS | 150000 | 18 | #2, #7 | 4.2? 4.3? 4.7? | REC. 15.12 REJ 16.01
11 | 1803 | RTAR | EHC | THE EFFECTS OF VENTILATION AND UVGI DEVICES ON THE INFECTION OF RESPIRATORY DISEASE IN STUDENTS DORMITORIES | 200000 | 24 | #11 | None | REC 16.05 REJ 16.06
12 | 1805 | RTAR | 1.4 | NEAR OPTIMAL THERMAL ENERGY STORAGE CONTROL SEQUENCES | 350000 | 36 | #3, #4 | None | REC 16.05 REJ 16.06
13 | 1813 | RTAR | 4.7 | DEVELOPMENT OF AN ACCURACY TEST METHOD FOR RESIDENTIAL ATTIC DUCT SYSTEM SIMULATIONS IN WHOLE-BUILDING ENERGY SIMULATION PROGRAMS | 200000 | 24 | #5 | None | REC. 16.08 REJ. 16.11
14 | 1822 | RTAR | 7.6 | ALTERNATE EXPRESSIONS OF BUILDING EUI AS ENERGY PERFORMANCE METRICS | 160000 | 24 | #1, #5, #7, #10 | None | REC 17.05 REJ 17.06
15 | 1826 | RTAR | 8.4 | BIO-INSPIRED LIQUID TO AIR HEAT EXCHANGER FOR HVAC&r APPLICATIONS | 225000 | 30 | #9 | None | REC 17.05 REJ 17.06
16 | 1828 | RTAR | 4.1 | FLOW CHARACTERISTICS OF INSTALLED FLEX DUCTS | 120000 | 24 | #1 | None | REC 17.05 REJ 17.06
17 | 1832 | RTAR | 1.4 | HVAC CONTROL LOOP PERFORMANCE DIAGNOSIS | 110000 | 15 | #1, #7 | None | REC.17.08 REJ. 17.10
18 | 1834 | RTAR | MTG. OBB | EXPLORE AND QUANTIFY BEHAVIOR-DRIVEN BUILDING ENERGY USAGE | 160000 | 18 | #1, #2, #7 | None | REC.17.08 REJ. 17.10

## Dropped Topics
DROPPED TOPICS FROM RESEARCH IMPLEMENTATION PLAN (The following topics have been dropped from the Research Implementation Plan for various reasons.)
# | TOPIC # | STATUS | RESPONSIBLE TC/TG/SSPC | TITLE | EST. COST | EST. DURATION (Months) | RESEARCH STRATEGIC PLAN GOALS SUPPORTED | CO-SPONSOR TCs | REASON FOR DROP | 1st DRAFT OF WORK STATEMENT DUE TO RAC BY THIS DATE | RAC APPROVAL FOR BID REQUIRED BY THIS DATE OR DROPPED |  | OBJECTIVE
= | = | = | = | = | = | = | = | = | = | = | = |  | =
1 | 1368 | RTAR | 4.5 | DEVELOP LOCAL CONVECTIVE HEAT TRANSFER COEFFICIENTS FOR INDOOR AND OUTDOOR SURFACES OF FENESTRATION SYSTEMS | 135000 | 24 | A6, C6 | None | Topic time expired from plan due to lack of activity. | 2009-05-15 | JULY 2011
2 | 1425 | RTAR | 4.3 | CHARACTERIZATION OF INFILTRATION, VENTILATION AND IAQ IN MID- AND HIGH-RISE MULTI-FAMILY BUILDINGS | 185000 | 24 | A1, B2 | None |  | 2008-05-15 | JULY 2010
3 | 1426 | RTAR | 4.3 | OCCUPANT RESPONSE TO THE NOISE OF RESIDENTIAL VENTILATION FANS | 100000 | 18 | A5 | None |  | 2009-05-15 | JULY 2011
4 | 1434 | WS | 10.5 | REFRIGERATED FACILITIES DOORWAY INFILTRATION AIR ENERGY REDUCTION | 250000 | 24 | A6, A8, C6, D1, D7, E1 | None |  | REQUIREMENT SATISFIED | EXTENDED TO JUL. 1, 2013
5 | 1435 | RTAR | 10.9 | OPTIMIZING BLAST FREEZER EFFECTIVENESS | 50000 | 18 | A6, A8, C6, D1 | None |  | 2008-05-15 | JULY 2010
6 | 1445 | WS | 2.1 | ENERGY CONSERVATION, AIR-CONDITIONING AND PRODUCTIVITY IN HOT-HUMID TROPICAL REGIONS | 175000 | 36 | A2, A7, B1, B2 | EHC 2.05 5.12 7.06 |  | REQUIREMENT SATISFIED | JULY 2010
7 | 1446 | RTAR | 3.4 | PHYSICAL PROPERTIES MEASUREMENTS OF CO2 / LUBRICANT MIXTURES | 75000 | 9 | D2, D3 | None |  | 2008-05-15 | JULY 2010
8 | 1465 | RTAR | 4.1 | THE DEVELOPMENT OF A COMPUTATIONAL FLUID DYNAMICS MODEL TO REPRESENT THE PERFORMANCE OF A ROUND FLOOR (SWIRL OR INDUCTION TYPE) OUTLET USED IN UNDERFLOOR AIR DISTRIBUTION | 100000 | 18 | C1, C3 | None |  | 2008-08-15 | OCT. 2010
9 | 1479 | RTAR | 3.6 | EVALUATION OF THE IMPACT OF A MONOCHLORAMINE DISINFECTION ON LEGIONELLA COLONIZATION OF AN INSTITUTIONAL SERVICE WATER SYSTEM AND ON THE INCIDENCE OF HEALTH CARE ASSOCIATED LEGIONNAIRES' DISEASE (LD) | 25000 | 24 | B2, B3, E1, E2 | None |  | 2009-05-15 | JULY 2011
10 | 1483 | RTAR | SSPC 90.1 | STANDARD 90.1 LINKED CRITERIA SLECTION ANALYSIS BASED ON PERFORMANCE WITH DESIGN PACKAGES | 250000 | 18 | A1, A5, A6 | None |  | 2009-08-15 | OCT. 2011
11 | 1494 | RTAR | 4.2 | PROCEDURES TO GENERATE HOURLY CLIMATIC DATA FROM SPARSE DATA SETS | 75000 | 12 | A6, C1, C6, E2 | None |  | 2009-05-15 | JULY 2011 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1496 | RTAR | 4.4 | MOISTURE TRANSPORT IN CONSTRUCTION MATERIALS & ASSEMBLIES AT LOW TEMPERATURES | 190000 | 24 | A6, B2, C2 | None |  | 2009-08-15 | OCT. 2011 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1497 | RTAR | 6.1 | VENT PERFORMANCE MODEL FOR ALL CATEGORIES, MULTI-STORY AND MULTI-UNIT FOR GAS & OIL FIRED FURNANCES, BOILERS AND WATER HEATERS | 150000 | 18 | C1, C3, D1 | None |  | 2009-08-15 | OCT. 2011 | The objectives of this project are: 1. Evaluate prior vent models (such as Vent II and OHVAP) and determine the status and availability of development, test, and validation documents, computer program source codes, and current relevance and scalability to the present and future venting needs discussed above. 2. Provide a unified and user-friendly software solution that satisfies the above identified needs. This software and supporting technical report represent the primary products of this work. 3. Identify areas where testing to confirm heat and mass transfer models and criteria for acceptable designs under transient conditions are needed. This can be used to guide a Work Statement for a subsequent project. 4. Provide recommendations for modernization of the venting requirements in codes, standards and ASHRAE handbooks | [8 empty] | 75000 | 75000
14 | 1498 | WS | 6.8 | OPTIMIZED DESIGN GUIDANCE FOR OUTDOOR AIR VENTILATION OF WATER LOOP HEAT PUMP SYSTEMS | 150000 | 18 | A1, A3, A5, A6, B1, C1, E1, E2 | None |  | REQUIREMENT SATISFIED | FEB. 1, 2014
15 | 1500 | WS | 5.3 | A DESIGNER'S GUIDE FOR THE SELECTION OF AIR TERMINAL UNITS | 120000 | 24 | A1, A2, A5, A6, B2, C1, C6 | None |  | REQUIREMENT SATISFIED | OCT. 1, 2011
16 | 1502 | TRP-R | 1.4 | USER INTERFACE DESIGN FOR ADVANCED SYSTEM OPERATION | 240000 | 24 | A7, B2, C6 | 7.09 | Replaced by URP-1633 after no bids received | REQUIREMENT SATISFIED | REQUIREMENT SATISFIED | To determine what information and system feedback the building engineering community is looking for and translate this into broad recommendations for performance specifications to support the engineering design, building operations and EMCS manufacturing communities. | [8 empty] | 90000 | 150000
17 | 1513 | RTAR | 10.3 | LIQUID/VAPOR SEPARATING VELOCITIES FOR INDUSTRIAL REFRIGERATION SYSTEMS | 100000 | 18 | D1, D2 | None | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | AUG. 15, 2010 | OCT. 2012
18 | 1514 | RTAR | 10.1 | THERMAL ENERGY RECOVERY FROM INDUSTRIAL REFRIGERATION SYSTEMS | 100000 | 12 | A7, D1, D2 | None |  | AUG. 15, 2010 | OCT. 2012
19 | 1543 | WS | 7.5 | DEMAND RESPONSE OPTIMIZATION PROTOCOL AND INTEGRATED TRAINING | 150000 | 18 | #2, #7 | None | Topic time expired from plan due to lack of activity. | REQUIREMENT SATISFIED | EXTENDED TO APR. 1, 2013
20 | 1545 | WS | 5.3 | NON-STEADY STATE OVERHEAD HEATING AND AIR CHANGE EFFECTIVENESS | 120000 | 24 | A1, B2, C6, C7, D1 | None | TC Dropped Topic | REQUIREMENT SATISFIED | JULY 2012
21 | 1548 | RTAR | 2.3 | IN-DUCT FULL-SCALE LABORATORY-EVALUATED COMPARISON OF PHOTOCATALYTIC OXIDATION (PCO) FILTERS VERSUS DRY-SCRUBBING MEDIA FILTERS | 150000 | 24 | A2, A5, B1, B3 | None | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | MAY 15, 2010 | JULY 2012
22 | 1563 | RTAR | 6.3 | IMPACT OF DUCT LEAKAGE ON INDOOR AIR QUALITY IN RESIDENTIAL SYSTEMS | 175000 | 18 | B2, B3 | None |  | AUG. 15, 2010 | OCT. 2012
23 | 1566 | WS | 8.1 | EQUATIONS TO ESTIMATE EVAPORATION RATES FROM WETTED SURFACES IN NATATORIUMS, COMMERCIAL AND INSTITUTIONAL BUILDING AND MEAT PROCESSING PLANTS | 300000 | 24 | A1, A6, A7, B2, C1, D1 | 1.12 8.12 |  | REQUIREMENT SATISFIED | EXTENDED TO JUL. 1, 2014
24 | 1573 | WS | 9.1 | DETERMINATION OF SUITABLE REPLACEMENT FOR SF6 WHEN USED AS A TRACER GAS IN ACCORDANCE WITH ASHRAE METHODS OF TEST 110 AND 129 | 125000 | 12 | #9, #8 | None |  | MAY 15, 2015 | JULY 2017
25 | 1576 | WS | 6.9 | TES SYSTEM PERFORMANCE METRICS RELATED TO CARBON EMISSION REDUCTIONS AT THE POWER GENERATION SOURCE | 100000 | 18 | A6 | 1.1 |  | REQUIREMENT SATISFIED | FEB. 1, 2013
26 | 1577 | RTAR | 8.4 | TUBE-TO-TUBE CONDUCTION EFFECTS IN FINNED TUBE HEAT EXCHANGERS | 200000 | 24 | C1, D2, D1, A1, A6, A7 | None |  | DEC. 15, 2010 | FEB. 2013
27 | 1610 | WS | 4.2 | DEVELOPMENT OF A TRANSPOSITION MODEL FOR CLEAR-SKY SOLAR IRRADIANCE | 35000 | 12 | A6, B2, C1, C6, D1 | 4.01 4.05 |  | REQUIREMENT SATISFIED | FEB. 1, 2014
28 | 1618 | WS | 9.6 | LITERATURE SEARCH AND RISK ASSESSMENT FOR ESTABLISHING A LOW LIMIT OF RELATIVE HUMIDITY LEVELS IN HEALTH CARE SPACES | 50000 | 6 | A1, A6 | None |  | DEC. 15, 2010 | FEB. 2013
29 | 1619 | RTAR | 9.9 | DATA CENTER GASEOUS CONTAMINATION LIMITS AND MEANS OF MONITORING | 180000 | 18 | A1, A5, D7, E1, E2 | None |  | DEC. 15, 2012 | FEB. 1, 2015
30 | 1623 | RTAR | 5.3 | DEVELOP A METHOD FOR TESTING THE MIST REMOVAL EFFICIENCY AND AIR FLOW RESISTANCE OF OIL MIST COLLECTORS | 150000 | 24 | #9, A1 | None |  | DEC. 15, 2013 | FEB. 1, 2016
31 | 1628 | RTAR | 3.4 | PHYSICAL PROPERTIES MEASUREMENTS OF HFO-1234yf / LUBRICANT MIXTURES | 100000 | 12 | #8, #9, D2, D3, D6 | None |  | AUG. 15, 2012 | OCT. 1, 2014
32 | 1635 | RTAR | 4.3 | SIMPLIFIED PROCEDURE FOR CALCULATING EXHAUST/INTAKE SEPARATION DINSTANCES | 50000 | 12 | #9, #10 | None |  | DEC. 15, 2012 | FEB. 1, 2015
33 | 1639 | RTAR | 1.4 | COMPARATIVE LAB AND FIELD EVALUATION OF BUILDING PRESSURE CONTROL METHODS | 199000 | 36 | #1, #2, #7, #9, #11 | SSPC 62.1 |  | AUG. 15, 2013 | OCT. 1, 2015
34 | 1653 | RTAR | 2.9 | QUANTIFY THE DEGRADATION OF CRITICAL HVAC COMPONENTS AND MATERIALS EXPOSED TO UVC LEVELS TYPICALLY USED IN HVAC SYSTEMS. | 75000 | 18 | #9, #4, #1 |  |  | AUG. 15, 2014 | OCT. 1, 2016
35 | 1657 | RTAR | EHC | EFFECTIVE VENTILATION SYSTEMS FOR AIRBORNE INFECTION ISOLATION ROOMS TO REDUCE POTENTIAL CROSS INFECTION | 250000 | 36 | #11 |  |  | AUG. 15, 2015 | OCT. 1, 2017
36 | 1664 | WS | 5.1 | CONDITIONING OF REPLACEMENT AIR FOR COMMERCIAL KITCHEN HVAC | 150000 | 18 | #1, #4, #5, #7 | None |  | MAY 15, 2014 | JUL. 1, 2016
37 | 1666 | RTAR | 5.3 | EXPERIMENTAL EVALUATION OF THE THERMAL AND VENTILATION PERFORMANCE OF STRATIFIED AIRE DISTRIBUION SYSTEMS COUPLED WITH PASSIVE CHILLED BEAMS | 195000 | 24 | #1, #2, #5, #7 | 4.07 |  | MAY 15, 2014 | JUL. 1, 2016
38 | 1680 | RTAR | 6.8 | INVESTIGATION OF THE ENVIRONMENTAL IMPACTS OF GROUND SOURCE HEAT PUMPS - DROPPED BY TC PER A14 RL REPORT | 75000 | 18 | #1, #3, #9 |  | TC Dropped Topic
39 | 1684 | RTAR | 9.1 | DISPERSION OF REFRIGERANT RELEASES TO CONNECTING SPACES VIA TRANSFER OPENINGS | 85000 | 15 | #1, #9 | SSPC 15 8.07 | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | MAY 15, 2015 | OCT.1, 2016
40 | 1685 | RTAR | 2.9 | FIELD STUDIES TO IDENTIFY THE BIOFILM MICRO-ORGANISIMS ON HVAC COOLING COILS AND IN DRAIN PANS. - DROPPED BY TC PER W15 RL REPORT |  |  |  |  | TC Dropped Topic
41 | 1690 | WS | 5.9 | INTERACTION OF TUNNEL VENTILATION PERFROMANCE WITH FIXED FIRE SUPPRESSION | 145000 | 15 | #7 | 5.06 | TC Dropped Topic FHWA will lead project instead | MAY 15, 2015 | JUL. 1, 2017
42 | 1697 | RTAR | 7.5 | REDUCE SIMULTANEOUS HEATING AND COOLING IN COMMERCIAL BUILDINGS | 150000 | 18 | #1, #7 | None | Topic time expired from display on plan due to no WS draft. TC can reactivate on plan by submitting WS draft and getting it approved by deadline noted in far left column | MAY 15, 2015 | JUL. 1, 2017
43 | 1700 | RTAR | 4.2 | A GLOBAL DATABASE OF MOISTURE DESIGN REFERENCE YEARS FOR HYGROTHERMAL ANALYSIS AND DESIGN OF BUILDINGS | 150000 | 24 | #1, #5, #7, #10 | None |  | MAY 15, 2015 | JULY 2017
44 | 1707 | RTAR | 2.6 | ANNOYANCE THRESHOLD OF TONES IN NOISE AS RELATED TO BUILDING SERVICES EQUIPMENT | 180000 | 24 | #4 | None |  | MAY 15, 2015 | JULY 2017
45 | 1731 | WS | 8.5 | HEAT TRANSFER PERFORMANCE OF MEDIUM PRESSURE ALTERNATIVE LOWER GWP REFRIGERANTS IN A FLOODED EVAPORATOR COMPRISING AN ENHANCED TUBE BUNDLE | 200000 | 24 | #8 | None | TOPIC DROPPED AFTER 4 YEARS ON PLAN AND NO ACTIVITY IN 2 YEARS
46 | 1739 | WS | 9.9 | DEVELOPMENT OF IMPROVED AND INTEGRATED ENERGY MODELING SOFTWARE FOR DATA CENTERS | 234250 | 18 | #2, #5 | None | WS DROPPED BY RAC AFTER 4 YEARS ON PLAN | NOT ON PLAN - RTAR STAGE SKIPPED
47 | 1744 | WS | 4.1 | GUIDELINES FOR ACCURATE CFD MODELING OF NATURAL VENTILATION | 250000 | 24 | #7 | None
48 | 1748 | WS | 4.07 | ASSESS AND IMPLEMENT NATURAL AND HYBRID VENTILATION MODELS IN WHOLE-BUILDING ENERGY SIMULATIONS (PHASE 2) | 180000 | 18 | #1, #3, #7 | None
47 | 1749 | WS | 1.5 | A BIM AND PHYSICS-BASED MODELING ENABLED PLATFORM FOR MONITORING AND VISUALIZING HIGH PERFORMANCE COMMERCIAL BUILDINGS | 200000 | 24 | #1, #6 | 7.3?
48 | 1758 | WS | 5.2 | CFD MODELING AND LABORATORY TESTING OF FLAT OVAL DIVERGING FLOW TEES TO DETERMINE LOSS COEFFICIENTS | 165000 | 24 | #1, #7 | None
49 | 1763 | WS | 4.7 | DEVELOPMENT OF AN IMPROVED TOOLKIT FOR ANALYZNG BUILDING ENERGY USE FROM TIMES SERIES DATA: UPDATE TO THE INVERSE MODEL TOOLKIT (RP-1050) | 160000 | 18 | #1, #3, #7 | None |  | TOPIC DROPPED AFTER 4 YEARS ON PLAN AND NO ACTIVITY IN 2 YEARS
50 | 1768 | RTAR | 1.11 | ASSESSMENT OF HVAC EQUIPMENT IDLE POWER CONSUMPTION AS A PERCENTAGE OF BUILT ENVIRONMENT ENERGY LOAD | 150000 | 24 | #5, #1 | None | RTARS TIME EXPIRED FROM PLAN AFTER 4 YEARS
51 | 1783 | RTAR | 7.5 | DEVELOP COST AND PERFORMANCE INDICES TO EVALUATE EFFECTIVENESS OF VIRTUAL SENSORS IN HVAC APPLICATIONS | 200000 | 24 | #1 | None